## Title Page
PPMP20008 Risk Register
Student Name: | <Student name>
Student Number: | <Student Number>
Contact details: | <Student email address and mobile phone number>
Domain: | <Domain Name>
Project Name: | <Project Name>
Document Purpose and Usage
This register is to be used to capture and analyse risks as outlined in the assessment criteria. Ensure that you complete all fields on this tab being the title page and the risk register tab. The remaining tabs provide you with information you may need to use to fill in the required fields, do not attempt to modify information in other tabs. Ensure that all entries are reflective of the project as described in your selected tender. This template has been adapted from the Department of Communities, Child Safety and Disability Services, Qld Govt, project log. We are greatly appreciative of the support from all our industry partnerships.

## Risk Register
PROJECT RISK & OPPORTUNITY REGISTER
Risk / Opportunity Identification | [5 empty] | Risk & Opportunity Analysis | [9 empty] | Post Treatment Risk & Opportunity Analysis
Number | Date Logged | Raised By | Status | Type | Description and Cause | Proximity | Theme | Category | Likelihood | Consequence | Level (pre treatment) | Treatment Response | Treatment | Treatment Update | Owner | Residual Impact | Likelihood (post treatment) | Consequence (post treatment) | Level (post treatment)
1 |  |  |  | Risk | Risk example - There is a risk that deployments could be delayed due to an aggressive schedule of critical releases over the next three months. |  |  | #N/A |  |  | #N/A |  | Example - Project Board to prioritise releases to avoid delays. | [5 empty] | #N/A
2 | [7 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
3 | [7 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
4 | [7 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
[8 empty] | #N/A |  |  | #N/A | [7 empty] | #N/A
Note on A3: This number is used for identification purposes.
Note on B3: Record date logged.
Note on C3: Name of the person raising the risk / opportunity.
Note on D3: To manage active or closed risks / opportunities. Closed risks / opportunities should not be deleted. They should be left to provide an audit trail.
Note on E3: Choose a type from the drop down list.
Note on F3: Describe the risk / opportunity. This should describe the source of the risk / opportunity. That is, the anticipated event or situation that gives rise to this risk or an event that would have a favourable impact if it occurred.
Note on G3: A measure of how soon the risk / opportunity may occur, days/weeks/months/years. If able to, provide a month and year.
Note on H3: Select theme from drop down list. To determine the theme refer to the consequence table.
Note on I3: Category will automatically be selected once the theme has been chosen.
Note on J3: Measure of the likelihood of the risk or opportunity occurring - refer to the Likelihood Scale Table .
Note on K3: Determine the appropriate level of impact. Refer to the Consequence Table. Note: For opportunities reverse the descriptions of the consequence table.
Note on L3: Calculated by the likelihood and consequence measurements. See Table 1 in the Reference Guide which describes the determined level
Note on M3: Determine how best to respond to the risk / opportunity by implementing an appropriate treatment. See Table 2 in the Reference Guide for explanations of each response.
Note on N3: Clearly describe the actions that are appropriate to treat this risk or harvest the opportunity.
Note on O3: Provide an update of the treatment. Insert dates for each new update. Effort to update treatment is dependant on severity of risk.
Note on P3: Person that has been assigned responsibility for the management and monitoring of this risk / opportunity.
Note on Q3: Describe the impact after the risk or opportunity has been treated.
Note on R3: The likelihood now that the mitigation strategy has been introduced
Note on S3: The consequence now that the mitigation strategy has been introduced
Note on T3: The level of risk / opportunity now that the mitigation strategy has been introduced

## Risk Categories Table
RISK CATEGORIES TABLE
Select the category that relates to the particular risk.
Note: When more than one category is applicable, select the category with the greatest consequence, as per the Consequence Table.
Risk category | Planing Priorities | Definition
Client & Community | Customer Service | Includes clients, stakeholders and the community and relates to our ability to be able to identify and respond to those people and organisations who may be affected by or perceive themselves to be affected by, a decision or activity undertaken by the department. Conversely the department needs to be able to identify any possible impact that client , stakeholder or community actions may have on the operation of the department
Stronger Partnerships
Business & Governance Processes | Innovation | All business processes other than financial and human resources and includes Information, information systems and information management. It relates to all of our internal business activities that we must excel at so as to ensure that we are continually adding value for our clients, stakeholders and the community
Simpler Process
Finance | Smarter Investment | All or any financial aspects and looks at how effective we are at being able to focus our limited resources effectively in order for us to achieve our targeted outcomes and strategic objectives.
People | Dynamic Workforce | All and any aspects of human resources and organisational development and considers what skills and competencies we need to develop, in order to meet our operational needs and to meet the expectations of our clients , stakeholders and the community now and in the future.

## Likelihood Scale Table
LIKELIHOOD SCALE TABLE
Note: If more than one description applies the highest rating is to be used.
Overall Likelihood Rating | Description | [1]Probability of event occurring | Historical Probability
Almost | Is almost certain to occur | Greater than 75% | Is almost certain to occur within the foreseeable future or within the programme or project lifecycle
Certain
Likely | Is likely to occur | 50% - 75% | Is likely to occur within the foreseeable future or within the programme or project lifecycle
Possible | May occur | 25% - 50% | May occur within the foreseeable future or within the programme or project lifecycle
Unlikely | Is not likely to occur | 10% - 25% | Is not likely to occur within the foreseeable future or within the programme or project lifecycle
Rare | Will only occur in exceptional | Less than 10% | Will only occur in exceptional circumstances
[1] Based on Financial Accountability Handbook, Queensland Treasury, July 2009

## Consequence Table
CONSEQUENCE TABLE
Category
Level of Impact | People | Financial/Procurement | Information/ICT | Performance/Service Delivery | Infratructure/Asset Management | Stakeholder/Community
Critical | • Sudden or unexpected loss of a number of key personnel • Loss of life, permanent disability or injury or multiple serious injuries • Ongoing lack of staff confidence and low staff morale across the organisation • Lack of understanding by staff of their obligation to work within specific legislative frameworks • Lack of understanding of a number of staff in relation to Code of Conduct | • Impact on >10% of budget OR >$5 Million (Whichever is the lessor) • Non delivery or loss of critical products, services or systems | • Loss of critical services, programs or data: • Non-recoverable loss of critical files, data or records | • State wide cessation of multiple services or programs greater than one month operational delay • Major program objectives not achieved | • Long term and permanent loss of critical asset/building | • Regular incidents of misinformation conveyed to community, stakeholders and staff
Major | • Low retention rates of key personnel Serious injury/ies requiring specialist medical treatment or hospitalisation or lost time of greater than four days. • Long term decline in staff confidence/morale • Lack of understanding by staff of their obligation to work within specific legislative frameworks • Lack of understanding of individual staff in relation in relation to Code of Conduct | • Impact on 5% -10% of budget OR $1million – $ 5 Million (Whichever is the lessor) • Severe delays or restrictions to key products, services or systems | • Severe restrictions to key services, programs or large loss or theft of data; • Severe restrictions to access critical files data or records | • Cessation of some services or programs; up to one month operational delay | • Sustained damage to asset property/facilities lasting many months | • Occasional incidents of misinformation conveyed to community and stakeholders
Moderate | • Inability to attract & retain key personnel in identified high demand roles or hard to fill locations • Injury requiring medical treatment or lost time of four or fewer days • Frequent decline in staff confidence/morale • Limited understanding by some staff of their obligation to work within specific legislative frameworks • Limited understanding of a number of staff in relation to the Code of Conduct | • Impact on 2%-5% of budget OR $500k - $1 Million (Whichever is the lessor) • Restrictions or disruption to delivery of products, services or systems | • Restrictions to operational services, programs & loss or theft of some data • Recoverable loss of critical files, data or records | • Cessation of some services or programs; up to one fortnight operational delay | • Significant but temporary damage to assets or property facilities | • Occasional incidents of inadequate internal communication with staff
Minor | • Difficulty recruiting or replacing officer/s in critical or key departmental positions within a reasonable timeframe • Minor injury requiring first aid treatment • Some Short term decline in staff confidence/morale • Some understanding by staff of their obligation to work within specific legislative frameworks • Limited understanding of individual staff in relation to Code of Conduct | • Impact on 1%-2% of budget OR $100k - $500k (Whichever is the lessor) • Minor disruption to delivery of products, services or systems | • Minor effect on services and/or programs • Loss of non-critical files, data or records | • Cessation of some services or programs; up to one week operational delay | • Slight / temporary damage to assets or property/facilities | • Isolated incidents of inadequate external communication with stakeholders and community
Insignificant | • Lack of suitable candidates to fill key operational roles within a reasonable timeframe • Isolated incidents of short term decline in individual staff confidence/morale • Isolated incidents of individual staff unaware of their roles and responsibilities in relation to Code of Conduct | • Impact on less than 1% of budget OR <$100k (Whichever is the lessor) • Temporary disruption to delivery of products, services or systems | • Temporary disruption to a service or program • Temporary loss of non-critical files, data or records | • Cessation of some services or programs; over 2 days operational delay | • Insignificant minor damage to assets or property/facilities (incident report only submitted) | • Isolated incidents of inadequate internal communication with staff

## Risk Matrix
Risk Matrix
Risk Tolerance
ê
­ | Rare | LOW | LOW | LOW | MEDIUM | HIGH
L i k e l i h o o d
| Unlikely | LOW | LOW | MEDIUM | MEDIUM | HIGH
| Possible | LOW | MEDIUM | MEDIUM | HIGH | HIGH
| Likely | MEDIUM | MEDIUM | HIGH | HIGH | EXTREME
| Almost Certain | MEDIUM | MEDIUM | HIGH | EXTREME | EXTREME
â
|  | Insignificant | Minor | Moderate | Major | Critical
¬ C o n s e q u e n c e ®

## Reference Guide
Table 1: Likelihood Scale Table
Description | Definition
Almost Certain | Is almost certain to occur within the foreseeable future or within the programme or project lifecycle
Likely | Is likely to occur within the foreseeable future or within the programme or project lifecycle (Probability of occurrence between 50 – 75%)
Possible | May occur within the foreseeable future or within the programme or project lifecycle
Unlikely | Is not likely to occur within the foreseeable future or within the programme or project lifecycle
Rare | Will only occur in exceptional circumstances
Table 2: Risk Treatment Responses
Description | Definition
Avoid (threat response) | Typically involves changing some aspect of the project, that is the scope, procurement process, supplier or sequence of activities, so that the threat either can no longer have an impact or can no longer happen.
Reduce - probability and/or impact (threat response) | Proactive actions taken to reduce the probability of the event occurring, by performing some form of control, and reduce the impact of the event should it occur.
Fallback - reduces impact only (threat response) | Putting in place a fallback plan for the actions that will be taken to reduce the impact of the threat should the risk occur. This is a reactive form of the 'reduce' response which has no impact on likelihood.
Transfer - reduces impact only, and often only the financial impact | Shifting responsibility for the risk to another partly, who ultimately bears some of the consequences if the risk occurs; for example through insurance or contractual indemnification arrangements. This may be done though specific clauses in the contract.
Accept (threat response) | A conscious and deliberate decision is taken to retain the threat, having discerned that it is more economical to do so than to attempt a threat response action. The threat should continue to be monitored to ensure that it remains tolerable.
Share (threat or opportunity response) | Modern procurement methods commonly entail a form of risk sharing through the application of a pain/gain formula: both parties share the gain (within pre-agreed limits) if the cost is less than the cost plan; and share the pain (again within pre-agreed limits) if the cost plan is exceeded. Several industries include risk-sharing principles within their contracts with third parties.
Exploit (opportunity response) | Seizing an opportunity to ensure that the opportunity will happen and that the impact will be realised.
Enhance (opportunity response) | Proactive actions taken to enhance the probability of the event occurring, and enhance the impact of the event should it occur
Reject (opportunity response) | A conscious and deliberate decision is taken not to exploit or enhance the opportunity, having discerned that it is more economical not to attempt an opportunity response action. The opportunity should continue to be monitored.
Poor or Non-existant | Ineffectual measures, not communicated, sparsely implemented and of little value.

## Lookups
Drop down look ups
Risk Register
Likelihood |  | Consequence |  | Risk Level |  | Status | Type | Category of risk impact
1.Rare |  | 1.Insignificant |  | 1. Low |  | Active | Threat | People | People
2.Unlikely |  | 2.Minor |  | 2. Medium |  | Closed | Opportunity | Finance/Procurement | Finance
3.Possible |  | 3.Moderate |  | 3. High |  |  |  | Information/ICT | Business and Governance Processes
4.Likely |  | 4.Major |  | 4. Extreme |  |  |  | Performance /Service Delivery | Business and Governance Processes
5.Almost Certain |  | 5.Critical | [5 empty] | Infrastructure/Asset Management | Business and Governance Processes
[8 empty] | Stakeholder/Community | Client and Community
| 1.Rare | 2.Unlikely | 3.Possible | 4.Likely | 5.Almost Certain
1.Insignificant | Low | Low | Low | Medium | High
2.Minor | Low | Low | Medium | Medium | High
3.Moderate | Low | Medium | Medium | High | High
4.Major | Medium | Medium | High | High | Extreme
5.Critical | Medium | Medium | High | Extreme | Extreme
Issue Register Value Lists
Issue Type |  | Severity
Request for Change |  | Critical
Off-Specification |  | Major
Problem or Error |  | Moderate
Risk Eventuating |  | Minor
Insignificant
Quality Register Value List |  |  | Product register Value Lists
QC Type |  |  | Approved | Deployment
Peer Review |  |  | In Progress | Deployment and Transition
Internal Walkthrough |  |  | In Review | Design
External Walkthrough |  |  | Not Started | Initiation
Inspection |  |  | Rejected | Patch deployment
Quality Review |  |  |  | Start up
Performance Test and Trials |  |  |  | Startup and Initiation
Maintenance Test |  |  |  | Transition
Stress Tests |  |  |  | Organisational Change and Training
Audit |  |  |  | Procurement
Program
Project
Specialist
Other
Lessons Learned Value Lists |  |  |  | Benefits Register
Category |  | Type |  | Financial - cost avoidance
Project Management |  | Strength |  | Financial - cost reduction
Quality |  | Weakness |  | Financial - revenue gains
Tool |  | Estimation |  | Service - improved productivity
Personnel |  | Opportunity |  | Service - enhancements (internal)
Other |  | Other |  | Service - enhancements (external)
Social
Risk - reduction
Risk - avoidance