## Dashboard
SuperFast IT Company
Proposed Greenfield Network
DASHBOARD
| Year: | 2019 |  | Release Date: | 2019-09-30
| Departments | 4
1 | TRANSMISSION NETWORK |  | 2 | ACCESS NETWORK |  | 3 | CORE NETWORK
4 | OTHER REQUIREMENTS
SUMMARY OF REQUIREMENTS
DEPARTMENT |  | Plan |  |  | FORECAST/ FUTURE PLANS
TRANSMISSION NETWORK |  | Design backbone links with a minimum of 40G throughput that is self healing and resilient |  |  | Backbone network must be upgradeable , scalable with minimum disruption to services
CORE NETWORK |  | Resilient core network |  |  | Core network deployement must be modular for scalability
ACCESS NETWORK |  | Connect four(4) different access networks using the best technology |  |  | All the access networks must be scalable with minimum disruption to services
OTHER REQUIREMENTS |  | As detailed in the requirements document |  |  | These must be adhered to throughout the project lifecycle

## TRANSMISSION NETWORK
SuperFast IT Company
Proposed Greenfield Network
TRANSMISSION NETWORK_1000
◄ Back to Main Page
| Link starting point | Site Abbreviation | Link Intermediate site | Link Intermediate site | Link Terminating point | Link Name | Link Abbreviation
1 | Perth | Prth | Mandurah | n/a | Bunbury | Perth-Bunbury | Prth-Bbry
1 | Bunbury | Bbry | Busselton | Nannup | Manjimup | Bunbury-Manjimup | Bbry-Mjmp
3 | Manjimup | Mjmp | ? | ? | Denmark | Manjimup-Denmark | Mjmp-Dnmk
4 | Denmark | Dnmk | ? | ? | Albany | Denmark-Albany | Dnmk-Alby
5 | Albany | Alby | ? | ? | Wagin | Albany-Wagin | Alby-Wgin
6 | Wagin | Wgin | ? | ? | Northam | Wagin-Northam | Wgin-Nthm
7 | Northham | Nthm | ? | ? | Joondalup | Northham-Joondalup | Nthm-Jnlp
8 | Joondalup | Jnlp | ? | ? | Perth | Joondalup-Perth | Jnlp-Prth
| Lancelin | Lnln | ? | ? | Joondalup | Lancelin-Joondalup | Lnln-Jnlp
9 | Joondalup | Jnlp | ? | ? | Lancelin | Joondalup-Lancelin | Jnlp-Lnln
| Equpment Type |  | Capacity (GB) | Site Name where equipment is Deployed | Fiber Type / Frequency used | Internal Equipment (amplifiers / DCMs)
10 | Fixed OADM |  | ? | ?
11 | ROADM |  | ? | ?
13 | 3R Repeater |  | ? | ?
14 | Transponder |  | ? | ?
15 | Muxponder |  | ? | ?
13 | Backhaul Radios |  | ? | ?
14 | 1R Repeater |  | ? | ?
15 | Muxponder |  | ? | ?

## ACCESS NETWORK
SuperFast IT Company
Proposed Greenfield Network
ACCESS NETWORK
◄ Back to Main Page
Network Name |  |  | Southern RAN_3000
Network Name |  |  | Highgate Network_3001
Network Name |  |  | Parks WAN Network_3002
Network Name |  |  | Joondalup Hospital Backup Link_3003
| Network | Southern RAN_3000
Site Name | Abbreviation | Details |  | Costing Model
East Bunbury | RAN_Est-Bbry | Full cellular network coverage to the next hop/ cell |  | This is a high priority access network
South Bunbury | RAN_Sth-Bbry | Full cellular network coverage to the next hop/ cell
Glen Iris (Bunbury) | RAN_GnI-Bbry | Full cellular network coverage to the next hop/ cell
Carey Park (Bunbury) | RAN_CyP-Bbry | Full cellular network coverage to the local area
Nannup Town Center | RAN_Twn_Nnp | Full cellular network coverage to the local area
Nannup Caravan Park | RAN_CrvP_Nnp | Full cellular network coverage to the local area
| Network | Highgate Network_3001
Site Name | Abbreviation | Details |  | Costing Model
Highgate POP | HGT_POP | POP must connect/ backhaul to Perth CBD core network |  | A cost -effective solution is needed to provision the required network
Chatsworth Properties | CHTSWTH | All properties from property 77 Chatsworth Road to 3 Chatsworth Road inclusive must have internet and data provisioned for
Stirling Properties | STRLNG | All properties from property 322 Stirling Street to 388 Stirling Street inclusive must have internet and data provisioned for
| Network | Parks WAN Network_3002
Site Name | Abbreviation | Details |  | Costing Model
Bakers Junction Nature Reserve | BJNR | Must be able to connect to services in Albany for the Parks HQ |  | This is a high priority site and must be implemented regardless of cost.
Mills Brook Nature Reserve | MBNR | Must be able to connect to services at Bakers Junction Nature Reserve
Gull Rock National Park | GRNP | Must be able to connect to services in Albany for the Parks HQ
Nilgen National Park | NGNP | Must be able to connect to services in Perth for the Parks HQ
Mount Mason Nature reserve | MMNR | Must be able to connect to services at Bakers Junction Nature Reserve
Mount ManyPeaks Nature Reserve | MPNR | Must be able to connect to services at Bakers Junction Nature Reserve
| Network | Joondalup Hospital Backup Link_3003
Site Name | Abbreviation | Required Capacity |  | Costing Model
Joondalup Hospital Backup Link | JHBL | Unlimmited data at 10GBPS Downstream and 1GBPS Upstream |  | This is a high priority site and must be implemented regardless of cost.

## CORE NETWORK
SuperFast IT Company
Proposed Greenfield Network
CORE NETWORK_2000
◄ Back to Main Page
Requirement Number | Network Requirement | Details
1 | MPLS Core in Perth | Very high capacity MPLS Core to support Triple Play- Voice, Data and Video using suitable technology . The MPLS core must have the capacity to support Metro networks in Perth urban areas
2 | Core Mirror | Mirror site to duplicate the minimum network components required in the event of a disaster at the main site
3 | Servers | Servers to enable the following functions: Content streaming, Access to the internet, Billing of customers, centralized authentication, authorization, and accounting (AAA) for wireless access network, realtime applications like banking applications
4 | VPN Tunnel | A bakery Peter Pie which has branches in Perth, Bunbury, Albany and Northham requires a service to connect their branch sites so information can be shared between branch sites. This information should not go over the internet for security reasons. A suitable VPN has to be provisioned for and configured for this purpose. Peter Pie have a separate Internet connection with a different service provider and they DO NOT need the VPN tunnel to connect to the internet
5 | Access Provision | Provision for different access technologies from fiber to radio waves and microwaves . There is no need to cater for copper access technology
6 | WAN Support | National Parks requires connections between their branch sites using suitable technology and connected as specified in the access network
7 | Other Equipment required | Network security devices
8 | Protocols supported | TCP/IP, OTN, HTTPS, DNS, DHCP, SNMP, IS-IS, BGP
9 | Upstream provison | SuperFast IT will have a connection/ connections to Tier 1 ISP/s for internet and bandwidth access
10 | Metro Network | Proposed Metro network connecting the following sites in Perth. Appropriate MPLS edge devices must be specified for use at each site. Each device to be capable of Triple play
11 | Interconnection agreements | SuperFast IT has an SLA with a tier 1 service provider and 2 interconnection arrangements with 2 Tier 2 telco service providers for cellular networks.
Metro Sites
Metro Site | Abbreviation | Services Supported
Joondalup | Core_Jnlp | VoIP, Data, RAN,
Caversham | Cvshm | VoIP, Data, RAN,
Morley | Morly | VoIP, Data, RAN,
Wangara | Wngra | VoIP, Data, RAN,
Duncraig | Dncrg | VoIP, Data, RAN,
Hazelmere | Hzlmr | VoIP, Data, RAN,
Iluka | Iluka | VoIP, Data, RAN,
Sorrento | Srnto | VoIP, Data, RAN,

## OTHER REQUIREMENTS
SuperFast IT Company
|  | Proposed Greenfield Network |  |  | 2018
SUSTAINABILITY
◄ Back to Main Page
Power
| Site | Power Option 1 |  | Power Option 2
1 | All Sites | Commercial power from Western Power |  | Suitable back up power
1
Other Considerations
| Consideration | Details
3
4 | Site Access | All site access to interconnection partners, private land must be received prior to the commencement of work
5 | Environmental Impact Assessment | Strictly no trenching in and around park lands for more than 100m. The 100m trenching can only be done to office buildings. Parks are protected by the Environment Protection Act which protects flora and fauna. All Parks and Nature reserves fall under this category of protection.
6 | WHS | WHS must be taken into account for every job undertaken. The following are required as part of the documentation on WHS and in accordance to the WHS Legislation and SafeWork Standards.
7 | Benchmarks | Perfomance benchmarks listed here
8 | Training | Training plan detailing training requirements
9 | Forecasting | Predict network perfomance and forecast traffic demands
Enterprise requirements
| Document | Recommended software/ system
10 | Design drawings, topology etc | MS Visio , Autocad, Corel Draw
11 | Project Management | PMBOK-PMI waterfall method, MS Project, Oracle Primavera P6
12
13
14