## ProjCrashing2010
Results
Data |  |  |  | Normal time | 12 |  | Minimum crash cost to meet project goal |  |  |  |  | 26000
Project goal | 8 |  |  | Minimum time | 7 | [5 empty] | Project time | 8
[5 empty] | Immediate Predecessors (1 per column) |  |  |  |  | Intermediate Computations
Activity | Normal Time (weeks) | Crash Time (weeks) | Normal Cost | Total Cost with Crashing | Immediate Predecessor (s) | Pred 2 | Pred 3 | Pred 4 |  | Crash weeks | Crash cost / week | Crash limit
A | 3 | 2 | 5000 | 10000 | [5 empty] | 1 | 5000 | 1
B | 2 | 1 | 3000 | 6000 | [5 empty] | 0 | 3000 | 1
C | 6 | 4 | 14000 | 26000 | [5 empty] | 0 | 6000 | 2
D | 5 | 3 | 10000 | 18000 | A |  |  |  |  | 1 | 4000 | 2
E | 7 | 5 | 11000 | 17000 | A |  |  |  |  | 1 | 3000 | 2
F | 2 | 2 | 8000 | 8000 | B |  |  |  |  | 0 | 0 | 0
G | 4 | 2 | 10000 | 24000 | C | D | F |  |  | 2 | 7000 | 2
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Precedence computations | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 if col precedes row | A | B | C | D | E | F | G | xxxxx | xxxxx
A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Normal time | 3 | 2 | 6 | 5 | 7 | 2 | 4 | 0 | 0
TimeFinish (variable) | 2 | 4 | 6 | 6 | 8 | 6 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
crash days (variable) | 1 | 0 | 0 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
limit | 1 | 1 | 2 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project time | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crash days | Finish Times for Tasks must be greater than finish for all predecessors | Finish A + T(row)-crash row | Finish B + T(row)-crash row | Finish C + T(row)-crash row | Finish D + T(row)-crash row | Finish E + T(row)-crash row | Finish F + T(row)-crash row | Finish G + T(row)-crash row
1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
1 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6
0 | 6 | 2 | 6 | 2 | 2 | 2 | 2 | 2 | 2
2 | 8 | 2 | 2 | 8 | 8 | 2 | 8 | 2 | 2
0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data
| Time | Precedence 1 | Precedence 2 | Precedence 3 | Precedence 4
A | A: 3; B: 0; C: 0; D: 0; E: 0
B | A: 2; B: 0; C: 0; D: 0; E: 0
C | A: 6; B: 0; C: 0; D: 0; E: 0
D | A: 5; B: A; C: 0; D: 0; E: 0
E | A: 7; B: A; C: 0; D: 0; E: 0
F | A: 2; B: B; C: 0; D: 0; E: 0
G | A: 4; B: C; C: D; D: F; E: 0
Results
Task | A: Early Start; B: Early Finish
A | A: 0; B: 3
B | A: 0; B: 2
C | A: 0; B: 6
D | A: 3; B: 8
E | A: 3; B: 10
F | A: 2; B: 4
G | A: 8; B: 12
| Project | 12
Early start computations
A | B: 0; C: 0; D: 0; E: 0
B | B: 0; C: 0; D: 0; E: 0
C | B: 0; C: 0; D: 0; E: 0
D | B: 3; C: 0; D: 0; E: 0
E | B: 3; C: 0; D: 0; E: 0
F | B: 2; C: 0; D: 0; E: 0
G | B: 6; C: 8; D: 4; E: 0
Late finish computations
| A | B | C | D | E | F | G
A | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
B | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
C | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
D | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
E | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
F | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G | 12 | 12 | 0 | 0 | 12 | 0 | 12 | 12 | 12
| 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0
| 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0
Project Management
Data
| Time | Precedence 1 | Precedence 2 | Precedence 3 | Precedence 4
A | A: 2; B: 0; C: 0; D: 0; E: 0
B | A: 1; B: 0; C: 0; D: 0; E: 0
C | A: 4; B: 0; C: 0; D: 0; E: 0
D | A: 3; B: A; C: 0; D: 0; E: 0
E | A: 5; B: A; C: 0; D: 0; E: 0
F | A: 2; B: B; C: 0; D: 0; E: 0
G | A: 2; B: C; C: D; D: F; E: 0
Results | D: 0
Task | A: Early Start; B: Early Finish; C: Late Start; D: Late Finish; E: Slack
A | A: 0; B: 2; C: -2; D: 0; E: -2
B | A: 0; B: 1; C: -1; D: 0; E: -1
C | A: 0; B: 4; C: -4; D: 0; E: -4
D | 2 | 5 | -3 | 0 | -5 |  | 3 | 2
E | A: 2; B: 7; C: -5; D: 0; E: -7
F | A: 1; B: 3; C: -2; D: 0; E: -3
G | A: 5; B: 7; C: -2; D: 0; E: -7
| Project | 7
Early start computations
A | B: 0; C: 0; D: 0; E: 0
B | B: 0; C: 0; D: 0; E: 0
C | B: 0; C: 0; D: 0; E: 0
D | B: 2; C: 0; D: 0; E: 0
E | B: 2; C: 0; D: 0; E: 0
F | B: 1; C: 0; D: 0; E: 0
G | B: 4; C: 5; D: 3; E: 0
Late finish computations
| A | B | C | D | E | F | G
A | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
B | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
C | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
D | -3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
E | -5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
F | 7 | -2 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G | 7 | 7 | -2 | -2 | 7 | -2 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | Total | 61000 | 109000
Note on A5: Project Management: Submodel = 3; Problem size @ 7 by 2