## Final Exam Part 2 start
Data Table
Work Package | Predecessor | Duration (weeks) | Early Start | Early Finish | Late Start | Late Finish | Slack | On Critical Path (Y/N)? | ES | Legend | EF
A | -- | 2 | [6 empty] | Slack
B | A | 2 | [6 empty] | LS | Duration | LF
C | A | 3
D | A | 4
E | B | 2 | [8 empty] | A
F | C | 3
G | D | 6
H | E,F | 2
I | E,F | 5
J | G,I | 1
K | H,J | 2
1 | What is the critical path?
2 | What is the projected length of this project (in weeks)?
3 | What is the impact on the project (and the project manager) of changing the duration of task H from 2 weeks to 6 weeks?